## Sheet1
Risk Name | Total Impact | Likelihood | Risk by Likelihood | Responsible | Impact Years | Calculation Basis | Updates | Date Added
Material costs worsen from May 2025 K-VAP status (VSI) | 1281000000 | 85 | 108885000000 | Lafrentz / Adam | 2027 - 2040 | $997 material cost decrease: $42,950 May 2025 K-VAP VSI vs $41,953 Aug. 2025 interim status; Unrealized risk of $2,536 identified | Material cost VSI improved since May 2025 K-VAP status due to Cost Sprint efforts; Risk identified in major components such as the battery pack based on supplier offers, LK4 prices, pre-assemblies and LV harnesses | 2025-07-01
Target sales and service model not viable | 8700000000 | 15 | 130500000000 | Thacker / Sitron | 2028 - 2040 | Vehicle revenue loss from MSRP % paid to dealer; Loss of incremental revenues (parts, service, accessories, connectivity, and others; Other incremental costs (higher warranty cost provision, corporate OpEx, IT) | Achieved licenses necessary to preserve goto-market optionality in California, Missouri, Illinois, Utah – enabling 50-state direct sales; Arizona and Colorado license application underway, licenses expected Q3-Q4 2025; ~47 states open for direct service | 2025-07-01
Localization costs for LK4 and EA211 FSI | 536000000 | 1 | 536000000 | Lafrentz / Adam | 2026 - 2028 | EA211: $157.3M initial invest + $57.7M for Silao expansion risk; LK4: $418.3M initial invest + $26.6M structure | Scout included invest in PR74.OP submission until agreement made by Group how funds should be accounted across Brands | 2025-07-01
Tariff risks on MEK from CAN, MEX, and EU sourcing | 382000000 | 8 | 3056000000 | Kodumudi | 2027 - 2033 | LK4 imports from EU→Mexico; Non-USMCA compliant EDU assemblies; 15% duty on imported CKD components from EU' Battery cell imports for 2028 and early 2029 | Updated tariffs on imported auto parts from EU to 15; Consider non-USMCA tariff risk of 27.5% on FR/RR EDUs w/Audi LK4 imports | 2025-07-01
Tariff risks on production equipment and supplier tooling | 142000000 | 8 | 1136000000 | Kodumudi / Wollinsky | 2026 - 2028 | Equipment tariff and forex risk: $89.6M | Risk considers NPV time effects | 2025-07-01