## risk
Risk Name | Total Impact | Likelihood | Risk x Likelihood | Responsible | Impact Years | Calculation Basis | Updates | Quarter
Material costs worsen from May 2025 K-VAP status (VSI) | -1281000000 | 85 | -1088850000 | Lafrentz / Adam | 2027 - 2040 | $997 material cost decrease: $42,950 May 2025 K-VAP VSI vs $41,953 Aug. 2025 interim status; Unrealized risk of $2,536 identified | Material cost VSI improved since May 2025 K-VAP status due to Cost Sprint efforts; Risk identified in major components such as the battery pack based on supplier offers, LK4 prices, pre-assemblies and LV harnesses | 2025-07-01
Target sales and service model not viable | -8700000000 | 15 | -1305000000 | Thacker / Sitron | 2028 - 2040 | Vehicle revenue loss from MSRP % paid to dealer; Loss of incremental revenues (parts, service, accessories, connectivity, and others); Other incremental costs (higher warranty cost provision, corporate OpEx, IT) | Achieved licenses necessary to preserve goto-market optionality in California, Missouri, Illinois, Utah – enabling 50-state direct sales; Arizona and Colorado license application underway, licenses expected Q3-Q4 2025; ~47 states open for direct service | 2025-07-01
Localization costs for LK4 and EA211 FSI | -536000000 | 100 | -536000000 | Lafrentz / Adam | 2026 - 2028 | EA211: $157.3M initial invest + $57.7M for Silao expansion risk; LK4: $418.3M initial invest + $26.6M structure | Scout included invest in PR74.OP submission until agreement made by Group how funds should be accounted across Brands | 2025-07-01
Tariff risks on MEK from CAN, MEX, and EU sourcing | -382000000 | 80 | -305600000 | Kodumudi | 2027 - 2033 | LK4 imports from EU→Mexico; Non-USMCA compliant EDU assemblies; 15% duty on imported CKD components from EU; Battery cell imports for 2028 and early 2029 | Updated tariffs on imported auto parts from EU to 15%; Consider non-USMCA tariff risk of 27.5% on FR/RR EDUs w/Audi LK4 imports | 2025-07-01
Tariff risks on production equipment and supplier tooling | -142000000 | 80 | -113600000 | Kodumudi / Wollinsky | 2026 - 2028 | Equipment tariff and forex risk: $89.6M | Risk considers NPV time effects | 2025-07-01
Material costs worsen from December 2024 K-VAP status (VSI) | -1700000000 | 75 | -127500000000 | Lafrentz / Adam | 2027 - 2040 | $2,095 material cost increase; $42,950 May 2025 K-VAP VSI vs $40,855 Dec 2024 K-VAP VSI | Strategic pivot to remove 4x2 and make 4x4 standard across all trims; Further MEK reductions in preparation (e.g. entry ADAS, CMF optimizations, 12V battery, cost sprint) | 2025-04-01
Target sales and service model not viable | -8700000000 | 15 | -130500000000 | Thacker / Sitron | 2028 - 2040 | Vehicle revenue loss from MSRP % paid to dealer; Loss of incremental revenues (parts, service, accessories, connectivity, and others); Other incremental costs (higher warranty cost provision, corporate OpEx, IT) | Achieved licenses necessary to preserve goto-market optionality in California, Missouri, Illinois, Utah – enabling 50-state direct sales; Arizona and Colorado license application underway, licenses expected Q3-Q4 2025; ~47 states open for direct service | 2025-04-01
Battery system sourcing threatens cost versus December 2024 K-VAP status | -342000000 | 60 | -20520000000 | Kodumudi / Adam | 2027 - 2040 | 10% battery system material cost increase vs December 2024 K-VAP VSI on 63 kWh EREV (10% increase on $4,107 battery system) | Battery cell decision planned for May 27 K-VAP; Pack sourcing in progress with initial pack supplier quotes above VSI | 2025-04-01
Factory commodity prices and supplier quotes above target versus December 2024 K-VAP status | -46000000 | 100 | -4600000000 | Wollinsky | 2023 - 2028 | Sustained market feecback; 100% likelihood of $46M infrastructure risk compared to December 2024 K-VAP | Included in CapEx risk | 2025-04-01
Localization costs for LK4 and EA211 FSI | -609000000 | 100 | -60900000000 | Lafrentz / Adam | 2026 - 2028 | Invest not accounted for in Group planning round; risk is considering NPV time effects | EA211: $167M; LK4: $537M initial invest + $82M structure | 2025-04-01
Scout’s environmental credit contribution to Group account is not as positive as PR74.SP |  | 100 |  | Decker | 2028 - 2040 | Scout BEV installation rate decreased from 49% to 24% ; Trump administration likely to reduce targets. Additional mitigation measures will be derived as needed based on new regulations | Scout’s Range Extender considered as part of PR74.SP submission with 51% share; updated sales mix will be reflected in PR74.OP with 76% EREV share; Environmental credit implications to be calculated and consolidated at Group level | 2025-04-01
Tariff risks on MEK from CAN, MEX, and EU sourcing | -198000000 | 80 | -15840000000 | Kodumudi | 2027 - 2040 | Sec. 232 tariffs on non-USA content for USMCA components has reduced in risk; IEEPA / Sec. 310 tariffs remain in effect on goods from China | Based on C-Price tariff risk of $238/car on a palette basis on China, India, SK goods | 2025-04-01
Tariff risks on production equipment and supplier tooling | -142000000 | 80 | -11360000000 | Kodumudi | 2026 - 2028 | Risk considers NPV time effects | Equipment tariff and forex risk: $89.6M; Supplier tooling tariff risk: $64.0M | 2025-04-01